CHALLENGE

- Rig owner had only 45 days in hand to complete

Major Overhaul on four nos. of CAT 35 series engines.

- Rig was located at Dubai Dry dock and the above

timeline included supply of required spares

- If the deadline was missed, there could have been

a delay of over 90 days. This could have been a huge

opportunity loss for the rig owner.

- Due to space constraint inside engine room, at a time

not more than two engines could be worked upon

- In a similar situation previously, the rig owner had

suffered 90 days deputation delay due to the inability

of the local service provider to finish the job on time.

SOLUTION

- Neptunus has been a preferred partner to this customer in India. The customer trusted Neptunus to handle this challenging assignment in the UAE.

- Neptunus’ project management team ensured mobilization of two service teams and delivery of required spares at site on time.

- The teams overcame some teething problems pertaining to cramped space and labour shortage to manage movement of critical components like the crankshaft, old power packs, alternators & other old spares.

- With the teams working almost 17 hours a day & with strong project management overhauling was completed on the 40th day. It took two more days to complete load trials & hand over the engines to the customer.

BENEFITS

- Rig owner deputed the rig on time and this enabled revenue of 90 days * $45,000 =  $4mn

- For the rig owner, the cost of engine overhauling by Neptunus was lesser than the local service provider.

- The rig owner could also protect his reputation by delivering on the commitment to the charterer.